## Slide 1
AKSHA SUPPORT CHATBOT
Development Plan
Ship the agents the backend already supports first — a phased build order sequenced by tooling readiness, not feature importance.
Source CHATBOT_SYSTEM_ARCHITECTURE.md · SUPPORT_CHATBOT_AGENT_CATALOG.md Branch Chatbot_Abhishek

## Slide 2
GUIDING PRINCIPLE
Sequence by backend readiness, not by feature wish-list
Every agent in the catalog already carries a backend-change label:
GREEN
Existing APIs cover it completely — build the agent now.
ORANGE
A small response or adapter change unlocks it.
RED
Needs new write paths, approvals, or audit infrastructure.
Building in that order means agent work is never blocked waiting on a backend team, and nothing that can mutate surveillance state ships before the approval and audit rails exist. Phase 1 ships value in weeks using only what's already deployed; Phases 2–3 are staged behind the specific backend work each agent needs.
Aksha Support Chatbot · Development Plan
02

## Slide 3
ROADMAP
Four phases, three of them gated by backend work
Phase 0
Foundation
Router, state graph, JWT trust boundary, typed tool registry, tests.
→
Phase 1
Green agents
7 read-only agents on APIs that exist today. Ship first.
→
Phase 2
Orange agents
Ship one at a time as each small adapter merges.
→
Phase 3
Red agents
Parked until approval + audit infrastructure is proven.
Aksha Support Chatbot · Development Plan
03

## Slide 4
PHASE 0 · BLOCKING
Platform foundation
NO AGENTS SHIP WITHOUT THIS
Chatbot service scaffold
New aksha-chatbot-api service — FastAPI + LangGraph, independent from the Node backend.
State & checkpointing
ChatbotState schema plus chat_threads / chat_turns / chat_checkpoints in MongoDB.
Router & formatter shells
Structured JSON routing output — the model never returns a free-form agent name.
Typed tool registry
Pydantic-validated tool schemas; allowlisted tool names and destination hosts.
JWT trust boundary
Reuse the existing Aksha-jwt HS256 secret via jose — no second identity system.
Streaming & tracing
SSE responses, correlation IDs, OpenTelemetry spans per router/worker/tool call.
Aksha Support Chatbot · Development Plan
04

## Slide 5
PHASE 1 · SHIP FIRST
Green agents — zero backend change
READ-ONLY
Help & Product Guide
Indexed docs / UserManual
Alert Investigation (basic)
/api/alert · /api/myAlert
Camera Operations
/api/camera · /api/camgroup
Live Monitoring
/api/active · Socket.IO
Insights & Analytics
/api/insight · /api/insightReport
Notification (read)
/api/notification
Multi-Language Support
chatbot layer only
Aksha Support Chatbot · Development Plan
05

## Slide 6
PHASE 1 · FRONTEND
Reuse ChatPopover instead of building a chat UI
Already exists
ChatPopover.tsx
• Dialog shell with message list • User / assistant bubble styling • Text input + send-on-submit • Chat history state management • Existing “download chat” action
→
To build
General chatbot widget
• Generalize the popover beyond investigation-only • Wire to new /api/chatbot/threads and /messages • Add source-citation rendering in message bubbles • Add streaming (SSE) token-by-token rendering • Surface clarification prompts as a distinct message type
Aksha Support Chatbot · Development Plan
06

## Slide 7
PHASE 2 · SHIP AS EACH ADAPTER LANDS
Orange agents — minor backend change
SMALL, SELF-CONTAINED CHANGES
Agent | Backend change needed
Alert Summary | Expose summary status + timestamp from a new per-alert/camera/day summary module.
Image & Anomaly Analysis | Extend image-analysis response with confidence, risk indicators, evidence references.
Camera Troubleshooting | Surface last-seen time, FPS, RTSP/service health from camera config.
KPI Report | Standardize KPI field names, units, reporting period, calculation timestamp.
Timeline & Sequence | One sortable schema for event, evidence, processing, notification timestamps.
Error Explanation absorbs the source docs' "Code Explainer" concept — operational codes only, not source code | No error-code catalog exists today — services return raw HTTP status + free-text messages. Define a small named vocabulary for camera/RTSP/pipeline errors, then expose it.
System Health | Authenticated health/dependency/resource endpoint with an observation timestamp.
Model & Detection | Read-only endpoint for active model version, supported classes, confidence thresholds.
Aksha Support Chatbot · Development Plan
07

## Slide 8
PHASE 3 · DEFERRED BY DESIGN
Red agents — parked until write infrastructure exists
MUTATES STATE
Video Retrieval
needs media search API
Incident Investigation
needs cross-camera correlation
False Positive & Feedback
writes review state
Camera Configuration
writes config, needs approval
Surveillance Control
start/pause/restart, needs approval
Notification Configuration
writes recipients/rules
User & Access
role/permission writes
Report Export
async jobs + masking
Compliance & Audit
needs immutable audit store
Escalation & Human Support
needs ticketing integration
MUST EXIST FIRST
• Approval-gate node with short-lived, argument-bound tokens • Idempotency keys on every write tool • chat_approvals and chat_audit_events collections • Role-based permission scopes enforced server-side • 100% unauthorized-action prevention on the security eval set
Aksha Support Chatbot · Development Plan
08

## Slide 9
CROSS-CUTTING
Risks the codebase audit surfaced
1
JWT scope is too thin
Only siteId + a single role string — no tenant_id, roles array, or camera scope.
2
Decoded JWT is never checked
req.user is set but no route filters data by role or site.
3
Mobile tokens likely fail verification
Signed with issuer 'mobile-app', verified against hardcoded 'algosign'.
4
Live credentials committed to the repo
client_secrets.json, credentials.json, plaintext RTSP creds, default Mongo root creds.
5
Insight/KPI data isn't in MongoDB
Flat JSON on disk or Azure Blob — needs dedicated file/blob adapters.
6
No error-code catalog exists
Every service returns raw HTTP status + free-text messages — Error Explanation needs a new taxonomy, not just exposure.
Aksha Support Chatbot · Development Plan
09

## Slide 10
RELEASE GATES
What "done" means per phase
Phase 0
Schema, permission, and checkpoint tests pass; JWT issuer bug fixed and scope-resolution verified.
Phase 1
All 7 agents live; tool-call validity ≥ 99% on the regression set; citation presence 100%.
Phase 2
Each new adapter covered by contract tests before its agent activates; no regression in Phase 1.
Phase 3
100% unauthorized-action prevention on the security set; approval + audit tested in staging.
Aksha Support Chatbot · Development Plan
10

## Slide 11
NEXT STEP
Start Phase 0 and Phase 1 in parallel
Foundation work (router, state, JWT fixes) and the seven green agents share no blocking dependency once the tool registry contract is fixed — they can be staffed as two concurrent workstreams.
Aksha Support Chatbot · Development Plan
11